## Sheet1
CODE |  | Page | Description | Platform | ASSIGNED TO | State | Note | Assigned by | Date assigned
TSAT001 | Copy | ALL | Change section name "Reg./Non-Reg" to "Investment Type |  | BR Clau | DONE
TSAT002 | copy | Investment Goals | Change bullets to this copy: Major purchase (i.e. House or car) Retirement Regular income Save earnings Other |  | BR Clau | DONE
TSAT003 | design | ALL | Evenly place section names on progress bar |  | BR Clau
TSAT004 | copy | Reg/Non-Reg | Change bullets to: Registered Plan (i.e. RRSP, TFSA, RESP, RDSP) Non-registered plan |  | BR Clau | DONE
TSAT005 | design | Amount | Remove slider on desktop view |  | BR Clau | DONE
TSAT006 | design | Amount | Add quantity indicators along the scroll bar |  | BR Clau
TSAT007 | UI | Term | Change input field to Select options |  | BR Clau | DONE
TSAT008 | design | Term | Remove slider on ALL views |  | BR Clau | DONE
TSAT009 | UI | Access Term | Change input field to Select options |  | BR Clau | DONE
TSAT010 | design | Results | "Based on your answers…" should be on one line |  | BR Clau | DONE
TSAT011 | design | ALL | Adjust progress bar to end at Results DOT |  | BR Clau |  | Visual bug to fix when progress reaches Results page
TSAT012 | design | Results | Remove "Visit product page" link and hyperlink product name instead |  | BR Clau | DONE
TSAT013 | design | Results | Add spacing around products data (Yield, investment, etc) |  | BR Clau |  | More to do: adjust alignment around buttons
TSAT014 | UI | Results | Remove "Next" button |  | BR Clau | DONE
TSAT015 | copy | ALL | Change Tool name to "Investment Selector" |  | BR Clau | DONE
TSAT016 | calculator |  | Apply minimum term length of 1 year when no default term and less than a year |  | BR Clau | DONE
TSAT017 | calculator |  | When recommending Index-Linked products: 1) Recommend the one with biggest min&max rate diff (excluding unlimited) 2) List the other products as additional recommendations 3) In case of equality, use priority list to determine first recommendation |  | BR Clau
TSAT018 | Graph | Results | Products that shouldn't display on graph have buttons in the graph legend |  | BR Clau
TSAT019 | Graph | Results | After changing answers, previously recommended products retain their graph visibility. Some graph lines are not linked to their respective "Display on graph" button either. |  | BR Clau
TSAT020 | Format | Amount | Formatting problems between display and number value. Ex: 1) Enter 50000. Exit field and it gets formatted to "$50,000" 2) Click again to edit and modify shown number "50,000" to "50,00". 3) Exit field, and the number gets formatted to "$50" (because of comma) |  | BR Clau
TSAT021 | Pages | Investment Goals | Remove this page |  | BR Clau |  |  | MERIDIAN | May 5
TSAT022 | Copy | Investment Type | Registered account to following order: TFSA,RRSP,RRIF,RESP,RDSP |  | BR Clau |  |  | MERIDIAN | May 5
TSAT023 | Copy | Account Type | Bullets in following order: TFSA,RRSP,RRIF,RESP,RDSP |  | BR Clau |  |  | MERIDIAN | May 5
TSAT024 | Design | ALL | Radio buttons are not full squares (design issue) |  | BR Clau |  |  | MERIDIAN | May 5
TSAT025 | Copy | Access to funds | Change bullet "No" for "No, I will not redeem my investment early" |  | BR Clau |  |  | MERIDIAN | May 5
TSAT026 | calculator | Results | Add product recommendation GTG HISA to scenario: term 1 or 2 years, no access, Guaranteed |  | BR Clau |  |  | MERIDIAN | May 5
TSAT027 | products | Results | Add note for mutual funds: "Please speak with a Meridian Advisor to find out more about our full suite of mutual fund products." |  | BR Clau |  |  | MERIDIAN | May 5
TSAT028 | products | Results | Add note for all indexed products: "Meridian has a variety of index-linked GICs to choose from, with some offering a guaranteed minimum rate" |  | BR Clau |  |  | MERIDIAN | May 5
TSAT029 | calculator | Results | Remove all recommendation of 5 year Escalator for non-reg scenario |  | BR Clau |  |  | MERIDIAN | May 5
TSAT030 | calculator | Results | Remove Ladder GIC when member chooses 4 year term and maybe access funds |  | BR Clau |  |  | MERIDIAN | May 5
TSAT031 | design | Results | Indexed product: add minimum and maximum rate placement |  | BR Clau |  |  | MERIDIAN | May 5
TSAT032 | copy | Results | Remove "Note:" before all messages for products |  | BR Clau |  |  | MERIDIAN | May 12
TSAT033 | design | Results | Increase font-size of the Notes |  | BR Clau |  |  | MERIDIAN | May 12
TSAT034 | chart | Results | Make the yAxis minimum be the investment sum. (there's a visual problem when a ILGIC has no minimum rate (0%) and the shading starts slightly above the investment) |  | BR Clau |  |  | MERIDIAN | May 12
TSAT035 | calculator | Results | No defautl CTA on products that don't contain CTAURL. Use: Contact Us http://www.meridiancu.ca/find-us/our-locations/Pages/default.aspx |  | BR Clau |  |  | MERIDIAN | May 12
TSAT036 | chart | Results | xAxis has weird breaks in time (91 days, 183 days, 274 days…) less that a year: break into quarter units 2-3 years: break into half years 4-5 years: break into whole year |  | BR Clau |  |  | MERIDIAN | May 12
TSAT037 | UX | Results | Make Product name click ability clearer (underline) |  | BR Clau |  |  | MERIDIAN | May 12
TSAT038 | products | Results | Update All ILGICs product links to their individual product page (see feedback document) |  | BR Clau |  |  | MERIDIAN | May 12
TSAT039 | calculator | Results | Please update calculator to adapt to these scenarios: • TFSA – 2 Year – Maybe – please remove 3 year Escalator as an option • TFSA – 2 Year – No – Guaranteed – please remove 3 year Escalator as an option • TFSA – 2 Year – No – Flexibility – please remove 3 year Escalator as an option • TFSA - 5 year – Maybe - please add mutual funds |  | BR Clau |  | Will need to extract the logic of these new scenarios and add them to the spreadsheet before modifying calculator | MERIDIAN | May 12
TSAT040 | calculator | Results | Min and Max range should both start at the investment amount at 0 years |  | BR Clau
TSAT041 | design/copy | ALL | Add info bubbles (By June 1st : https://bluerushmedia.basecamphq.com/projects/13118288-meri-001-meridian-calculators-phase-1/posts/98016063/comments#344484666) |  | BR Clau |  |  |  | May 25
TSAT042-CR | calculator | Results | Update scenarios to new logic: https://bluerushmedia.basecamphq.com/projects/13118288-meri-001-meridian-calculators-phase-1/posts/98172272/comments Waiting on calc confirmation Monday May 30) |  | BR Clau |  |  |  | May 18
TSAT043 | copy | ALL | There are two periods in the first sentence of the disclaimer. |  | BR Clau |  |  | MERIDIAN | June 7
TSAT044 | copy | Account Type | Please insert an additional line with the Help text here that indicates “Please speak with an Advisor before selecting the Registered Plan that’s right for you.” |  | BR Clau |  |  | MERIDIAN | June 7
TSAT045 | copy | Term | Update ‘this funds’ to ‘these funds’. In title |  | BR Clau |  |  | MERIDIAN | June 7
TSAT046 | copy | Access to funds | Update ‘Would you’ to ‘Will you’ in title |  | BR Clau |  |  | MERIDIAN | June 7
TSAT047 | calculator | Results | ‘Good to Grow High Interest Savings Account’ – I’m assuming this is the new RRIF HISA? It won’t be in production until the September Release … is it ok that we are advertising it as an available option now? |  | BR Clau |  | Create test cases in calculator: what is the product can't be pulled from Rates? | MERIDIAN | June 7
TSAT048 | copy | Results | 5.2 The RIFS product should be labelled ‘Advantage Savings Account (RRIF) in order to follow suit with both the RRSP and TFSA variable options |  | BR Clau |  | Non-issue: we are pulling the names from Meridian Rates | MERIDIAN | June 7
TSAT049 | ILGICs | Results | 6.1 The yield provided for the ILGICs is for the total period, not annualized. Meridian will provide the annualized rate, rather than the yield over the term as the minimum/ maximum rates in the rate table that is used to update the calculator rates. This is consistent with all the other products using annualized rates. Blue Rush needs to take no action as the formulas are accurate, but I wanted to provide this as an FYI to Blue Rush and the other stakeholders. |  | BR Clau |  | FYI from Meridian - need to confirm if this will eventually require implementation as CR | MERIDIAN | June 7
TSAT050 | ILGICs | Results | 6.2 The performance starts at $0.00 on the vertical axis whether it is a minimum rate guarantee or no minimum rate product. Suggest starting the performance on the vertical axis at the minimum rate: (see table in Word document) Based on the change in 6.1 (TSAT049), Blue Rush needs to adjust the calculator to calculate the cumulative rate, based on the annualized rate provided in the rate table, to display the cumulative rate guarantee in the graph. |  | BR Clau |  | Need explanation AND calculator modification | MERIDIAN | June 7